## Admin
S.No | Application | URL | User Id | Password
1 | Employee Id |  | BACS11788/506591 | Arp@2022
2 | Laptop |  | gaurav.tugnawat | Garvit@1234
3 | HCM | https://apachcm.exelatech.com/ | 506591 | Tugnawat@1234 | Vijaya@1234
4 | HCM Time Log | https://cee-apac.exelatech.com/ | Email
5 | BEATS | https://beatsglobal.com/SourceHOV/BLogon.aspx?ReturnUrl=%2fSourceHOV%2fWorkItemListing.aspx | Email | Exela@2024
6 | BancTec Portal | http://apps.banctecindia.in/
7 | Payroll | http://trachrms/easypay/view/loginmain.aspx?
8 | Payroll Open Network | https://hcmpay.exela.global/EasyPAY/view/loginmain.aspx | ESS/0001/BACS11788 | S1@1
9 | TIMO | https://support.timo.global/#/login | Email | P@1234
10 | Self Service Portal | https://selfservice.exelaonline.com/showLogin.cc | gaurav.tugnawat | Garvit@1234 | yogesh/orange
11 | Self Help Portal | https://selfhelpad.exelaonline.com/showLogin.cc
12 | PRS (BancPay) | https://exelap2p.exelatech.com/BancPay/BPLogon.aspx?ReturnUrl=%2fBancPay%2fWorkItemListing.aspx&Login=true | Email | Garvit@1…. | garvit
13 | Kiteworks (DTF SAET sharepoint) | https://dtf.secureft.sa.gov.au/w/f-0919031e-f448-4d11-a395-bc15cf8fd98f | Email | T@1…
14 | Dataroom | https://dataroom.exela.global/#/ | Email | T@1...
15 | Uploadit | https://uploadit.exelatech.com/ | Email | P@1…
16 | GIT Url | https://216.9.112.155/users/sign_in | GTugnawat | _4UvMlj71V/G%
| GIT New Url | https://corp-git-02.exelaonline.com/ | GTugnawat | _4UvMlj71V/G%
17 | Jira SAET | https://jira.exelatech.com/login.jsp | pranitisharma | Oct@2019
18 | Time Log | https://cee-apac.exelatech.com/Index | Email | S1@1
19 | BPOTS | https://bpots.exelatech.com/bpots/index.php?r=srnCcd/admin&srnA=SRN&tab=scosrn&page=att#srnatt | Exelaonline\gaurav.tugnawat | Exela@1234#
20 | meeting Link | https://exelaonline.webex.com/meet/gaurav.tugnawat
21 | Net Extender | SHA.EXELA.GLOBAL:4433 | gaurav.tugnawat | 8Xt<4}N#V+4A@ | hovservices.com
22 | Dry Sign | https://drysign.exelatech.com/signDocument?key=ziu1cZ3aCLyNkWUVELfUJEhW7&locale=en | Mail | Garvit@1234
23 | Admin | .\btecIT or .\ExelaIT |  | D#v$loper1
24 | JIRA AmRest | https://jira.exelatech.com/secure/Dashboard.jspa | Devika Pawar | Devikap12#
25 | Jenkins | http://10.182.208.74:8080/login?from=%2F |  |  | Net extender
26 | Escrow TIMG account | https://escrow.timg.com/ | SAET | Re2M5gPkj6
27 | Microsoft Account | https://portal.azure.com/ https://outlook.office.com/ | gaurav.tugnawat@banctec.onmicrosoft.com | Garvit@2023
28 | google | Gmail Account | Email auth. | Tugnawat@2023
29 | Google shared drive (Mailboat) | https://drive.google.com/drive/folders/0AGu4cz_v4zVAUk9PVA
|  | https://drive.google.com/drive/folders/1kjKmJLXzMiwBjO9zt-WDJNyVDzlM1M5y | Devika
30 | Google shared drive (AmRest) | https://drive.google.com/drive/folders/1HIvt2RHoPlutjLPQ2DiLnM3zQ4LLy_sV
31 | New Microsoft Account 0365 | https://dev.azure.com/ExelatechCloud/PSG/_git/mailboat-auth | gaurav.tugnawat@exelatech.cloud | Raz31560 | Shravan1@1
32 | Azure devops | https://dev.azure.com/ExelatechCloud | same as above
https://dev.azure.com/ExelatechCloud/PSG/_git/trugreen-mobile-ui
33 | GCP Jump Box | Login throug IAP | gcp/gaurav.tugnawat J8!F8vtKw1($q4aIA
34

## Attendance
Resource Name | 2024-01-24 | [30 empty] | 2024-02-24 | [30 empty] | 2024-03-24
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | T | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | T |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | T
Tejas Phalak | [24 empty] | H | [5 empty] | 1 | [29 empty] | 5 | [29 empty] | H |  |  | 1
Praniti Sharma | [24 empty] | H | [5 empty] | 0 | [29 empty] | 1 | [29 empty] | H |  |  | 2
Pavan Kumar | [24 empty] | H | [5 empty] | 2 | [29 empty] | 4 | [29 empty] | H |  |  | 7
Omkar | [24 empty] | H | [5 empty] | 9 | [29 empty] | 0 | [29 empty] | H |  |  | 2
Varad | [24 empty] | H | [5 empty] | 1 | [29 empty] | 0 | [29 empty] | H |  |  | 2
Gopal Gote | [24 empty] | H | [5 empty] | 3 | [29 empty] | 0 | [29 empty] | H |  |  | 2
Devika Pawar | [24 empty] | H | [5 empty] | 0 | [29 empty] | 0 | [29 empty] | H |  |  | 0
Pankaj C | [24 empty] | H | [5 empty] | 0 | [29 empty] | 1 | [29 empty] | H |  |  | 1
Gaurav Tugnawat | [24 empty] | H | [5 empty] | 1 | [29 empty] | 0 | [29 empty] | H |  |  | 2
Harish Upadhya | [24 empty] | H | [5 empty] | 0 | [29 empty] | 1 | [29 empty] | H |  |  | 11
Sagar Bharuka | [24 empty] | H | [5 empty] | 1 | [29 empty] | 2 | [29 empty] | H |  |  | 8
Resource Name | 2024-04-24 | [30 empty] | 2024-05-24
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | T | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | T
Tejas Phalak | [8 empty] | H | [22 empty] | H | [11 empty] | H
Praniti Sharma | [8 empty] | H | [22 empty] | H | [11 empty] | H
Pavan Kumar | [8 empty] | H | [22 empty] | H | [11 empty] | H
Omkar | [8 empty] | H | [22 empty] | H | [11 empty] | H
Varad | [8 empty] | H | [22 empty] | H | [11 empty] | H
Gopal Gote | [8 empty] | H | [22 empty] | H | [11 empty] | H
Devika Pawar | [8 empty] | H | [22 empty] | H | [11 empty] | H
Pankaj C | [8 empty] | H | [22 empty] | H | [11 empty] | H
Gaurav Tugnawat | [8 empty] | H | [22 empty] | H | [11 empty] | H
Harish Upadhya | [8 empty] | H | [22 empty] | H | [11 empty] | H
Sagar Bharuka | [8 empty] | H | [22 empty] | H | [11 empty] | H
Saurabh Pathare | [31 empty] | H | [11 empty] | H
Resource Name | 2024-10-24 | [30 empty] | 2024-11-24
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | T | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | T
Tejas Phalak | [31 empty] | H
Praniti Sharma | [31 empty] | H
Pavan Kumar | [31 empty] | H
Omkar | [31 empty] | H
Varad | [31 empty] | H
Gopal Gote | [31 empty] | H
Devika Pawar | [31 empty] | H
Pankaj C | [31 empty] | H
Gaurav Tugnawat | [31 empty] | H
Harish Upadhya | [31 empty] | H
Siddharth Ovhal | [31 empty] | H
Note on CD12: Author:
Note on AT17: Author: election day

## Resourcing
S.No | Resource Name | Emp. ID | SAET | AmRest | MailBoat | Farmers | TrueGreen | Designation | Skills | Lap/Desk | Number
1 | Gaurav Tugnawat | BACS11788 | 20% | 50% | 30% |  |  | PM |  | Laptop
2 | Tejas Phalak | BACS11704 | 40% | 30% |  |  | 30% | TL |  | Laptop | DLP144
3 | Praniti Sharma | BACS9912 | 50% |  |  | 50% |  | TL-QA |  | Laptop | Exela-LPT-294
4 | Gopal Gote | BACS12202 |  | 100% |  |  |  | SSE |  | Desktop | INMH-PN-DT4269
5 | Devika Pawar | BACS11968 |  | 100% |  |  |  | Tester |  | Desktop
6 | Pankaj Chafekande | BACS11496 |  | 100% |  |  |  | SE | Java,Angular,Mongo,Node | Desktop
7 | Pawan Kumar | BACS11674 | 100% |  |  |  |  | SE | Java,Springboot,Sql | Desktop | INMH-PN-DT7024
8 | Varad | BACS11646 | 100% |  |  |  |  | SE | Java,Springboot,Sql | Desktop
9 | Onkaar | BACS12011 | 100% |  |  |  |  | Tester |  | Desktop | INMH-PN-DT4066
10 | Sagar Bharuka |  |  |  |  | 50% | 50% | SE | MEAN,JAVA,MONGO | Desktop
11 | Harish Upadhya | BACS12366 |  |  | 20% | 40% | 40% | SSE | JAVA, Springboot, SQL | Desktop
|  |  |  | Project | Team Size
|  |  |  | AmRest | 5
|  |  |  | SAET | 6
|  |  |  | MailBoat | 4

## CR
S.No | Date | Project | CR No | BEATS ID | Description | Status | Priority | Devlopment Hrs | PM Hrs | Total Hrs | Costing AUD | USD | Development Dates | Resource | Action Points | Remarks | Development Updates
1 | 2023-12-29 | SAET | CR-077 | CR24044AM0005 | Automatically generate documents from parent to child case | Live | 1 | 84 | 25 | 109 | 26825 | 17436.25 | Planned Start Date:- 26-Feb-24 Planned End Date:- 29-Mar-24 Actual Prod Date:- 21-Mar-24 | Varad | Query response awaited from SAET | Estimates provide to SAET-8-Feb | CR-077 Production Deployment is on 21-Mar-24
2 | 2023-12-29 | SAET | CR-073 | CR24044AM0016 | CaseVision plugin compatibility with the latest version of Adobe Acrobat Reader | In-Progress | 2 | 72 | 22 | 94 | 23150 | 15047.5 | Start Date:-27-Mar-24 End Date:-12-Apr-24 Actual Prod Date:-15-Apr-24 (4th Apr) | Pavan | Team to identify the solution and send a holding response to the SAET | Estimates provide to SAET-30-Jan | QA deployment is planned for 22-Mar-24
3 | 2023-12-29 | SAET | CR-075 | CR24044AM0003 | Remove Pending Correspondence | In-Progress | 3 | 76 | 23 | 99 | 24375 | 15843.75 | Start Date:-16-Apr-24 End Date:- 3-May-24 | Varad | Received Query response from SAET. Exela to send the effort estimates | Estimates provide to SAET-8-Feb | Development Completed, Code Review Completed, Buddy Testing Pending
4 | 2023-12-29 | SAET | CR-076 | CR24044AM0004 | List of Notes on Case Summary | In-Progress | 4 | 84 | 25 | 109 | 26825 | 17436.25 | Start Date:- 6-May-24 End Date:- 23-May-24 | Pavan | Received Query response from SAET. Exela to send the effort estimates | Estimates provide to SAET- 10 Jan | Development Started
5 | 2023-12-29 | SAET | CR-074 |  | Using CaseVision with MS Edge InPrivate mode | In-Analysis | 5 |  |  |  |  | 0 | Discard |  | Require further Analysis as the change seems not possible with the current Angular 4 version. | Exela to send Effort estimates
1 | 2024-03-13 | SAET | CR-0771 A |  | Additional Modification of cases on top of CR-077 | Live | 1 | 24 | 7 | 31 | 7625 |  | Live on 21-Mar-24

## Infra
Project SAET
S.No | Env | URL | User Name/Pwd | Server Name | Location | Port | Version
1 | QA | http://10.182.207.110:8080/SAETCMS/#/login | Appro/Appro
2
Project AmRest
S.No | Env | URL | User Name/Pwd | Server Name | Location | Port | Version
1 | UAT | https://boxoffice-uat.exelatech.com/#/login | Devika.Pawar/ Password123
2 | Database | Dev:- AmRestEFA_Dev, BoxOffice_Dev, ExelaAuth_Dev
QA:- AmRestEFA, BoxOffice_QA, ExelaAuth_QA
Project MailBoat
S.No | Env | URL | User Name/Pwd | Server Name | Location | Port | Version
1 | Prod | https://mymailboat.com/login.do | Admin User: Loginname: SFIWorkflow5010 Password: Mau@654321 |  | Testuser1/Harish@123
Standard User: Loginname: Billie Test2 Passwprd: 53bdc8f4-8
1 | UAT | https://sfi.boxoffice.global/SFIException/login.do | Admin user - username - admin_uat_sh password - 306d3c5b-a Standard user - username - user_uat_sh password - 8a29d5bd-5 |  | SFIapprover / Pa$$w0rd
| QA | https://mailboat-qa.exela.global/SFIException/login.do |  | Old QA | http://10.182.207.41:9080/SFIException/login.do | username - SFIadmin password - Sagar@1234
2 | Dev | http://10.182.207.107:8080/mailboatui/#/login | gaurav.tugnawat/shri/Password123
3 | DB | VM IP 10.182.207.64
| Dev | mongodb://BOXOFFICE:BOXOFFICE@10.182.207.64:27017/Mailboat-Dev
| QA | mongodb://BOXOFFICE:BOXOFFICE@10.182.207.64:27017/Mailboat-QA
4 | SVN | https://prodsvn.exela.global/prod/Asia/rdh/boxoffice/branches/SFI_Workflow/ | gauravtugnawat/Changem8!
5 | Google Docs | https://drive.google.com/drive/folders/1epYezKS18eExyon4l08WLnSI3z70Zm7x
| New Dev | http://10.182.207.107:8080/boxofficeui/#/login | Devika.Pawar/Password123
7 | new UAT | https://mailboat-sfi-uat.exela.global/mailboatui/#/login
| New QA | https://mailboat-sfi-qa.exela.global/mailboatui/#/login | gaurav.tugnawat/Welcome321
| GCP Storage | stb-mboat-x-us-e45900a8a4
| VM | vm-mboat-x-us-e4
| UAT | Ticket No 4599480
| SQL MS | MySQL DB QA Url=jdbc:sqlserver://10.182.158.45:1433;databasename=BoxofficeDB UserName=boxofficeadmin Password=Exela#2022 | sqlUser": "mailboat", "sqlPassword": "F029D31D-E6", "sqlDatabase": "BoxofficePreProdD
UAT
1. mailboat-sfi-uat.exela.global => http://localhost:8080/mailboatui/#/login
2. mailboat-sfi-uat.exela.global/auth => http://localhost:3110
3. mailboat-sfi-uat.exela.global/core => http://localhost:3111
4. mailboat-sfi-uat.exela.global/ingester => http://localhost:3112

## AmRest
S.No. | Date | JiRA ID | Issue Description | Raised By | Action On | Daily Update | Status | Remarks
1 | 2023-11-20 |  | DM team does not have the access to the servers after MFA to support | Gaurav | Ritesh | 20-Nov:- Mail sent to Vijay Nanhe and Ritesh for the updates. | Closed
2 | 2023-11-20 | AM-346 | TBD on Year end changes and Plan | Gaurav | Gaurav | 7-Dec: Fixed working 11-Dec:- Plan for 31st Dec | Closed | Mail Sent on 11-Dec
3 | 2023-11-22 |  | 29-Nov Release for Bug fixes. | Gaurav | Devika/Tejas | 28-Nov:- | Closed
4 | 2023-11-22 |  | Creation of Test cases of mailboat | Gaurav | Devika | 29-Nov:- | Closed | Injestion work flow is pending
5 | 2023-11-29 | AM-338 | Update Angular Version | Gaurav | Pankaj | 29-Nov:- | Hold | Upgraded but facing small CSS issues
6 | 2023-11-30 |  | Beats for Mail boat | Gaurav | Gaurav |  | Closed
7 | 2023-11-30 |  | Can we have Jira for Mailboat | Gaurav | Gaurav |  | Closed | Will Use TIMO and BEATS
8 | 2023-12-13 |  | AmRest Year end changes | Gaurav | Gaurav | Mail Sent on 18-Dec-23 | Closed | Mail to Ritesh with details and schedule a call.
10 | 2023-12-27 |  | Env Specific checklist | Gaurav | Devika/Gopal | Create for QA/UAT/Prod | In-Progress | GT to review
11 | 2023-12-28 |  | Gopal Machine issue | Gopal | Gaurav |  | Closed | Machine Replaced
12 | 2024-01-03 |  | Export Date is not updating in ES | Devika | Gopal | Config changes required | Closed
13 | 2024-01-05 | AM-359 | Fresh desk status is not updated for few documents | Devika | Gopal | Fixed | Closed | Deployed to Production
14 | 2024-01-15 |  | Document not send to Ambuy | Devika | Devika |  | Closed
15 | 2024-01-16 |  | QA and Dev Database Upgrade | Gaurav | Gaurav | Need to plan | In-Progress
17 | 2024-01-16 |  | New VAT implementation | Judyta | Gaurav | Requirement not clear. | Closed | Nothing on DMS as of now
18 | 2024-01-16 | AM-362 | Docs not processed in ES. | Devika | Gopal | Fixed | Closed | Prod Planned for 19-Jan
19 | 2024-02-01 |  | Mailboat demo to HelpDesk team | Gaurav | Sagar | GT to schedule a meeting on 7-Feb | Closed
20 | 2024-02-05 |  | Review Use case for Mailboat | Gaurav | Devika |  | Closed | Reviewed
21 | 2024-02-07 |  | New Mailboat documents required from Production | Gopal | GT/TP | Need to check with Sagar to fetch the latest documents from Prod. | In-Progress | Need the documents.
22 | 2024-02-09 | AM-366 | Low Disk space on exsevboap01, exsevboap02 | Devika | Devika | 2 Mongo DB Backup files created on 8th/8th Feb 2024. Need to raise a ticket to DM team to get details on the new backup created | Closed | BPOTS 4165661 Raised exsevboap01:- EFA Server and no new files are getting generated so no issues exsevboap02: Mongo DB where 2 Backup files need to be removed
24 | 2024-02-13 |  | Security Testing of JWT | Devika | Devika |  | Closed | Testing Passed On local env.
25 | 2024-02-14 |  | Memory issue in new mailboat QA server (New Url), Truegreen is also not working. | Tejas/Devika | Gaurav/Tejas |  | Closed | Taken separately with Mailboat team
26 | 2024-02-15 | AM-367 | Missing Data on CZ and SK | Devika | Devika |  | Closed | FF issues
27 | 2024-02-16 |  | Parsing the env variable from CMD | Gopal | Gopal |  | Closed | Fixed
28 | 2024-02-27 |  | BEATS Tickets need to update | Gaurav | Devika |  | Closed | BEATS updated
29 | 2024-02-28 |  | Node application deloyment on Linux server | Gaurav | Gopal | Need to discuss with Harish | Hold
30 | 2024-03-04 |  | Mongo Db server migration to Atlas | Gaurav | Gopal/Tejas | Need to Discuss with Ritesh | In-Progress | PRS Rasied
31 | 2024-03-07 |  | Mailboat QA App server space to be increased | Gopal |  |  |  | We will use the Dev FE for the QA for a time being.
32 | 2024-03-11 | AM-370 | Prod/UAT env was down | Devika | Devika | Fixed | Closed | Sweden's Prod server was down, UAT server restarted
31 | 2024-04-04 |  | Document XML portion is missing | EU | Devika | FF Issue data mismapped | Closed | XML data is missing.

## SAET
S.No. | Date | Issue Description | JiRA ID | Env | Raised By | Action On | Daily Update | Status | Remarks
1 | 2023-11-20 | CaseVision outlook plug-in not working since 17-Nov-23 | SC-1186 | PROD | ABD | Tejas | 20-Nov:-1. Outlook Plug-in not installed on UATIssue replicated. 2. QA V4 is working and we are waiting for ABD to provide access to system to check logs 21-Nov:- 1. requested Bharat to provide new plug-in setup with logs. (New Build) 2. No response from ABD. 22-Nov: - New plugin setup sent to ABD to check and team will capture the logs 27-Nov:- PRS for o365 is in progress | Completed | SAET security policy caused the issue by which plugin API was not getting called.
2 | 2023-11-20 | DTF Team is migrating DMZ server on 27-Nov-23 at 7 PM AD time |  | PROD | ABD | Gaurav | 20-Nov:- Planned for 27th Nov | Completed | Tejas/Praniti will support from App team
3 | 2023-11-22 | Make a list of feature/Component which mention impact of not having MS-Office/O365 |  | PROD | Anit | Gaurav | 22-Nov:- Check CR069 requirement and copy paste + Plugin related changes | Hold | Gaurav to coordinate with Praniti/Tejas
4 | 2023-11-22 | Require existing FTP Access |  | ALL | Anit | Praniti/Tejas | 22-Nov:- Approved by infosec | Completed | Request completed on 1 Dec.
5 | 2023-11-23 | Quartely service report and schedule a meeting |  | ALL | Anit | Gaurav/Praniti | Praniti to create a report and Gaurav to schedule a meeting 5-Dec: Schedule a meeting for 9th jan. | Completed | Include Point that current release delayed due to AGD transition.
6 | 2023-11-30 | SFTP test on Linux for Mailboat |  | QA | Anit | Tejas | 12 Dec: Tejas to check on Mailboat linux server. | Hold | In case we have to move from windows to linux
7 | 2023-12-04 | SAET CMS Prod Slowness reported on 4-Dec-23 | SC-1190 | PROD | ABD | Praniti | 4-Dec: Team tested on Prod and no issues, ABD also tested and was no issues 5-Dec: Will continue monitoring today. API calling is taking time. 12-Dec: Can not check as Account is expired | In-Progress | Monitoring in Progress
9 | 2023-12-22 | Schedule a call with John for CR074 | CR074 |  | Praniti | Praniti |  | Completed | Call Cancelled because of John's unavailability
10 | 2023-12-22 | Release 1.73 |  | PROD | Praniti | Praniti | Total 15 Fixes/CR004 planned for 29th-Dec-23 7PM ADT/2PM IST | Completed | Approval received from SAEt on 28th-Dec
14 | 2023-12-28 | API Refactor Periodically |  | PROD | Gaurav | Gaurav |  | Hold | Application Performance
15 | 2023-12-29 | CR073- CaseVision plugin compatibility with latest version of Adobe Acrobat Reader |  |  | ABD | Tejas/Praniti | 3-Jan: Analysis Completed | In-Progress | Solution not identified
20 | 2024-01-02 | Security vulnerability issue reported |  |  | Security | Praniti | 2-Jan: Mail send to Casevision Product team 4-Jan: Mail received from product team and the same has been sent to SAET. | Completed | *Alban Response sent to SAET.
21 | 2024-01-03 | Release 1.74 preparation (Major) |  |  | Praniti | Team | 1. Total fixes : 16 2. Planned for 9 Feb. Require client confirmation on UAT approved | In-Progress | Deployed to UAT and Testing is in progress
22 | 2024-01-10 | Microsoft 0365 Account (Blocking us in testing) |  |  | Praniti | Gaurav/Anit | Need to progress with this PR. Ticket No. 4064153 PRS: 233349300P008000015 | In-Progress | we need to push this else release would be impacted 1.74
23 | 2024-02-05 | CR-003- Delete Party |  |  | Praniti | Gaurav | Need to provide response to ABD | In-Progress
24 | 2024-02-13 | Release Tracker 1.75 preparation |  |  | Praniti | Onkar | 21-Feb:- Deployed to UAT on 21-Feb | In-Progress
25 | 2024-02-27

## MailBoat
Sno. | Date | Issue Description | Action On | Daily Update | Status | Remarks | Sr. No. | Actions | Sr. No | Sub-actions | Status | ET(In Days) | Remark
1 | 2024-01-23 | Mailboat Document not showing on List view | Gaurav | 23-Jan-24:-Meeting with Mark and Catherine | Closed | Issue was with the document upload | 1 | Analyse sql schema |  |  | Completed | 3
2 | 2024-01-23 | Application Support group and email id needs to be corrected | Gaurav | 1. Need to create a new DL and the Timo tickets need to be created | Closed | Need to Discuss with Anit | 2 | Design the mongoDB schema based on sql schema |  |  | Completed | 1
3 | 2024-01-23 | Get the Architecture Flow Diagram or else we have to create | Gaurav | 14-Feb:- We have Arch Flow diagram | Closed | Diagram | 3 | Export SQL data using utility | 1 | Utility MongoDB connection | Completed | 1
4 | 2024-01-23 | Mail from Amit Pathade regarding support line | Gaurav |  | Closed | TBD with Anit |  |  | 2 | Utility SQL connection | Completed | 2 | Facing Connection issue with SQL
5 | 2024-01-23 | Get the BEATS Resource access | Gaurav |  | Closed | Time sheet and Admin |  |  | 3 | Fetch data from sql multiple tables using queries | Completed | 2
6 | 2024-01-25 | Production data is not sync with SVN | Gaurav | 14-Feb:- | In-Progress | Will try to get it sysnc with new migration | 4 | Transform SQL Data | 1 | Conversion of multiple json object into single record for mongoDB | Completed | 2
7 | 2024-02-07 | Identify the number of users of Application | Harish | 14-Feb:- Ticket raised | In-Progress | Pending with Rule 14 - Ravindra no update as of now | 5 | Import tranformed data into mongodb | 1 | Cron creation for data insertion in mongoDB | Completed | 2
8 | 2024-02-07 | Retention period of the documents | Harish | 14-Feb:- Ticket raised | In-Progress | Pending with Rule 14 - Ravindra no update as of now | 6 | Import data into elasticsearch | 1 | Fetch data from mongoDB | Completed | 1
9 | 2024-02-07 | Avg no. of documents per month | Sagar | 14-Feb:- Need to Raise Query to DB team | Closed | Avg 2k Per month ( Database team sent a sheet) |  |  | 2 | Check data duplication in ES | Completed | 2024-01-02
10 | 2024-02-01 | Meeting with Helpdesk team to handover L1 support | Gaurav | Meeting scheduled for Monday 5th Feb 4 PM | Closed |  |  |  | 3 | Insert data in Elasticsearch | Completed | 2024-01-02
11 | 2024-02-01 | MailBoat support group needs to be created in TIMO | Gaurav | 14-Feb:- MailBoat group is created | Closed |  | 7 | Validate and test database | 1 | Validate and test mongoDB database | Not Started | 2024-01-02
12 | 2024-02-07 | production Database Schema | Gaurav |  | In-Progress | Gaurav to check With Rule 14 Team |  |  | 2 | Validate and test Elasticsearch data | Not Started | 2024-01-02
13 | 2024-02-13 | Get Production SFTP server access | Gaurav | Need to raise Ticket |  | Gaurav to get access | 8 | Test the application with Mongodb & ES database |  |  | Not Started | 1
14 | 2024-02-14 | MailBoat QA memory space issue | Harish | 14-Feb:- Ticket has been raised | In-Progress | No Update as of now
15 | 2024-02-21 | MailBoat Local environment working setup | Gaurav | Local: WIP Dev: No Dev QA:- Not working Ticket Raised UAT:- Working | Not Started | Create a plan
16 | 2024-03-05 | Ticket 4198822 -SFM reported not receiving the email notification to reset their password in Mailboat. | Gaurav
17 | 2024-04-18 | MailBoat Migration | Gaurav | PRS= 241099300P008000060 |  | Ticket Number= 4572900

## Jfrog
S. No | Task to perform | Status | Remark | Url if any | Ticket No. | Dependency if any
1 | Raise a Jfrog Repository access | Done | NA | https://exela.jfrog.io/ui/repos/tree/General/PSG-maven-virtual | NA | NA
2 | Create a Repo mailboat-npm-Virtual & amrest-npm-local | In-Progress |  |  | 45128232 | NA
3 | get access for the team | In-Progress |  |  | 45128232

## Mine
S.No | Project | Task Description | priority | Updates | Status | Remarks
1 | MailBoat | Log4J vulnerability issue | Critical | 26-Feb:- We further tried to set up a workspace however identified that it requires a change in the existing spring jars we are currently using. | Completed | 27-Feb:- progress made after spring 4 Jar updation but still getting dependency errors 12-Mar:- Not able to create a running workspace because of the version dependency. As of now, we are pushing to migrate the application to Boxoffice 2.0 21-Mar:- On Hold as we are planning to upgrade the application
2 | MailBoat | MailBoat Migration to BoxOffice 2.0 | High | Development completed and code deployed and tested on Dev environment | Completed | 7-Mar:-Implementation plan sent to Anit 12-Mar:- Demo meeting with client scheduled for 13 Mar. 21-Mar:- Mail sent Mark for approval to raise PRS 27-Mar:- MailBoat user document and recording sent to Mark
3 | MailBoat | L1 & L2 Support | Medium | Email Sent to Mark and Kethy and the required support is in place | Closed
4 | MailBoat/Farmers | Database to be migrate under Our DB team | Medium | Discussed this yesterday with the Rule 14 and and Ritesh's team. It was suggested that our team send them an email mentioning Farmers support will be with Rule14 and Mailboat will be supported by Ritesh's team | Closed | 27-Feb: Farmers ticket should be assign to Ravindra Vishwasrao team and Mailboat tickets to Ritesh's team
5 | SAET | CR-074 | High | SAET-CR-074 efforts estimates email sent for review | Closed | Effort estimates sent to SAET
6 | AmRest | exsevboap02 server low disk space | Medium | Replied to the Bhala's email and added DBA support team to suggest | Closed | 27-Feb:- Discussed with Rajan/Sumeet and they are working on the ticket and will update 28 Feb: TIMO 4178119 created for server team. Disk space increased
7 | Team | Performance Appraisal | Medium | 1-2-1 Is completed with the team | Closed | Submitted 3 Pending with others newly assigned
8 | SAET | SAET CR74 Scheduled Plan creation | Low | 4-Mar: MPP created and shared with Anit 7-Mar:- CR-074 added in consolidated MPP and sent to Anit for review | Completed | 21-Mar:- Approval awaited from SAET
9 | MailBoat | MailBoat new QA url is not working | High | 29-Feb:- Java 8 installed by the server team. Corrected to the java 7. Issue still exist and under WIP 1-Mar: Ticket 4194055 raise for SSL issues. Linux team | Completed | 12 Mar:- Need to follow up on the ticket 4194055 21-Mar:- Still need to check. Harish is on leave full week.
10 | AmRest | Mongo Db server to be migrated on Atlas | High | 4-Mar:- Replied to Ritesh's email. We will continue this discussion in another mail thread opened for the same. 5-Mar:- BPOTS 4199280 raised for the same | In-Progress | 5-Mar:- PRS required 12 Mar:- PRS 240729300P008000019 created.
11 | SAET | Get BEATS access to the SAET CRs | Medium | 5-Mar:- TIMO Ticket 2419533 has been raised | Closed | will get access once assigned by Anit
12 | SAET | QSR invite to be sent to SAET | Medium | Scheduled for 4th April 24 | Completed | 12 Mar:- Invite sent for 4th April 21:- Need to send the Service Deck.
13 | MailBoat | Production issue:- Reset Password link | Critical | 6-Mar:- BPOTS Ticket 4198822 raised for fetching required logs 7-Mar: TIMO ticket 2420353 raised as per the request | Closed | Workaround provide to Customer
14 | MailBoat | Email notification services not working | Medium | Need to debug through the code | Completed | 12 Mar: Code received from Vedant, Tejas to simulate and confirm 21-Mar:- Require further investigation.
15 | MailBoat | QA Server space issue | Low | require space to deploy new Mailboat changes to the QA environment. | Completed | 21-Mar:- New QA instance require provision
16 | SAET | CR-077 modification request | Medium | Effort analysed | Closed | 12 Mar:- Mail to be send to SAET with the effort estimates and request for a new CR 21-Mar:- Need this to be in BEATS
17 | ALL | GITLAB Troy sunset On June | High | We need to identify the another SVN to plan with | Completed | Need to discuss with Anit
18 | MailBoat | MailBoat Infra diagram for GCP | High | Require for GCP request | Not Started | Can refer truegreen document